## Sheet1
Sprint No. | Sprint Goal | Sprint Tasks | Start Date | End Date | Scrum Master | Daily Stand - up 1 | Daily Stand - up 2 | Daily Stand - up 3 | Sprint Review
1 | Creating Chatbot | Research on Rasa chatbot Figure out what is the specific case we are going to use Start to create chatbot (Work on analyze, design, implement, test and evaluation) Make a sketch of the predicted conversations (Check Design for correctness and requirements) Make personation skeleton Check python programming standards | 2024-10-12 | 22/12/2024 | Omidu | Date: 10/12/2024 Meeting Time: 17.00 Discussion of: What real life field we were going to implement our program into. Research on Chat Bot and all the requirements relating to it. Evaluating and finding a solution for those requirements. | Date: 16/12/2024 Meeting Time: 18.00 Discussion of: Looking through our functional requirements and preparing stories accordingly and gathering information about functionality, designs and additional requirements. | Date: 22/12/2024 Meeting time: 17.00 Discussion of: Data collection for training our chat bot. Reviewing our stories and finding some more possible scenario. Checking the python programing standards for our codes and going through other people's way of making chat bot. And making a brief of presentation skeleton | Stories we made were good and the codes we wrote for our chat bot was running but we had a slight problem on using other's dataset for training our bot. So we decided to use the easy way of training our bot. We had a nice skeleton for our presentation but we had some problems in choosing which parts to include in the slides and which not to.
2 | Connecting chatbot with facial recognition | Research on Face recognition algorithm Start to work on Facial Recognition and emotion detection part (Analyse, design, implement, test and evaluation) Test it using data sets (Check Design for correctness and requirements) Check python programming standards | 23/12/2024 | 2025-04-01 | Kasun | Date: 23/12/2024 Meeting Time: 17.00 Discussion of:How to connect our chat bot with facial recognition. Analysing facial recognition algorithms. Making a plan to work on the code and collection of data set what type of data should be tested, etc. | Date: 29/12/2024 Meeting Time: 17.00 Discussion of: Going through our codes and making designs for our program. Implemented our program with a clear images and it worked. We found a way to connect our chatbot with facial recognition. Gather dataset for testing | Date: 04/01/2025 Meeting Time: 17.00 Discussion of: Analysing and evaluation our program. Test results were positive. | Reviewing our program and comparing it with our requirements. Analysing and evaluation our program. Test results were positive. Making some changes on the comments on our code.
3 | Finish off the presentation. | Practicing the presentation Give each other feedback and review the details we are talking about in each slide | 2025-05-01 | 2025-06-01 | Manuja | Date: 05/01/2025 Meeting Time: 17.00 Discussion of: Final checks of the presentation. Final checks of the coding. Complete table of individual contributions. Complete the reference slide. | Date: 6/11/2024 Meeting Time: 17.00 Discussion of: Reviewing the order of slides Dedicating the slides for each person of the group Coming up with the scripts. |  | We have been able to fully complete the presentation. We have been able to make all the checks and final tests of the presentation slides and the codes in the scripts and will finish this in the scrum closure.
Scrum Closure | Presentation practice and final checks. Submit the work. | Practicing the presentation. Give each other feedback and reviewing the detail we are talking aboutin each slide. | 2025-07-01 | 2025-08-01 | Kasun | Date: 7/01/2025 Meeting Time: 17.00 Discussion of: Start practicing the presentation. Provide feedback to the team and improvements on what can be said and mentioned in the slides. | Date: 08/01/2025 Meeting Time: 17.00 Discussion of: Final practice of the presentation. Submission of the project. |  | We have finished off our project. We have practiced the presentation multiple times while timing ourselves to make sure that we can present everything within the 15 minutes timeframe. We have also submitted the project before the final deadline.